## Slide 1
HITBOX · PLATFORM
Build Investment
Proposal
End-to-end development plan, timeline, and budget for the Hitbox music-collectibles platform.
Prepared for: Executive Leadership
May 2026

## Slide 2
HITBOX
THE PRODUCT
Authenticated, evolving music collectibles.
Each physical collectible carries a cryptographic NFC chip. Owners scan it with the Hitbox mobile app to verify authenticity, register ownership, and unlock evolving digital value as the item is traded.
1
Authenticate
Tap-to-verify NFC chip with cryptographic ownership proof.
2
Collect
Personal vault, portfolio value, and collection insights.
3
Trade
Peer-to-peer trades and a public marketplace with live drops.
4
Evolve
Items gain XP, rank, and unlocks each time they change hands.
2 / 8
Hitbox Platform · Build Investment Proposal

## Slide 3
HITBOX
SCOPE OF WORK
Three connected systems, one platform.
Mobile App
iOS + Android (Flutter)
NFC scan & cryptographic verification
Personal collection & portfolio
Trades, social feed, notifications
Drops, wishlists, in-app purchase
Web Marketplace
Public storefront (Next.js)
Browse collectibles, artists, and drops
Marketplace listings and checkout
Artist landing pages and SEO
Account, profile, and transaction history
Backend Platform
Cloud services (Firebase + Functions)
Ownership ledger & evolution engine
Authentication, payments (Stripe), media
Admin tools, moderation, analytics
APIs shared by mobile and web
3 / 8
Hitbox Platform · Build Investment Proposal

## Slide 4
HITBOX
DEVELOPMENT APPROACH
Seven phases, milestone-based.
1
Discovery & specification
Requirements, technical architecture, fixed-bid scope.
3–4 wk
2
Design system & UX
Figma flows, every screen state, brand-aligned design system.
5–6 wk
3
Backend platform
Database, auth, ownership ledger, evolution engine, APIs.
8–10 wk
4
Mobile build (iOS + Android)
Flutter app, NFC integration, full feature set, store-ready.
16–20 wk
5
Web marketplace
Next.js storefront, listings, checkout, SEO, deploy pipeline.
12–16 wk
6
QA, security & IP audit
Test coverage, NFC crypto audit, performance, accessibility.
4–6 wk
7
Launch & stabilization
App Store review, soft launch, monitoring, hotfix window.
4 wk
4 / 8
Hitbox Platform · Build Investment Proposal

## Slide 5
HITBOX
TIMELINE
Approximately 9 months end-to-end.
Backend, mobile, and web tracks run partially in parallel.
M1
M2
M3
M4
M5
M6
M7
M8
M9
Discovery
Design
Backend platform
Mobile build
Web marketplace
QA & security
Launch
Setup
Backend
Frontend
5 / 8
Hitbox Platform · Build Investment Proposal

## Slide 6
HITBOX
INVESTMENT
$350,000 recommended budget.
Range: $300k (lean) to $425k (US senior team). Figures assume external contractor build.
Chart: 
| Discovery | Design | Backend | Mobile | Web | QA & security | Launch
Cost by phase ($k) | 25 | 35 | 65 | 110 | 70 | 30 | 15
TOTAL BUILD
$350k
over ~9 months
ONGOING (post-launch)
$8–12k / month
Maintenance, hosting, App Store + Stripe fees, on-call coverage.
6 / 8
Hitbox Platform · Build Investment Proposal

## Slide 7
HITBOX
DELIVERABLES
What you receive at launch.
✓
Native iOS + Android apps
Published to the App Store and Google Play, with NFC scan and full collector experience.
✓
Public web marketplace
Production deploy on Vercel, custom domain, SEO baseline, marketing pages.
✓
Backend platform
Firestore data model, Cloud Functions for evolution and trade logic, Stripe payments live.
✓
Admin & ops tools
Internal dashboard for catalog, drops, moderation, refunds, and analytics.
✓
Design system
Figma library and documented brand system handed over for ongoing work.
✓
Documentation & handover
Architecture docs, runbooks, security posture, deployment guide, source code repos.
7 / 8
Hitbox Platform · Build Investment Proposal

## Slide 8
HITBOX
RECOMMENDATION
Approve a $350k, 9-month build.
Engage an external development partner under a milestone-based contract. Stage funding by phase to retain control at each gate.
1
Approve discovery & design budget ($60k) to begin Phase 1–2.
2
Issue RFP to three vetted development partners; select on fixed-bid Phase 3+.
3
Lock contract structure: milestone-based, IP-assigned, with 10% retention.
4
Stand up monthly steering review for budget, scope, and risk.
5
Target soft launch in Month 9, full public launch in Month 10.
8 / 8
Hitbox Platform · Build Investment Proposal