## Slide 1
HITBOX · PLATFORM
From Prototype
to Production
What we’ve already built, and the investment needed to ship Hitbox to launch.
Prepared for: Executive Leadership
May 2026

## Slide 2
HITBOX
WHERE WE STAND
A working platform — not a sketch.
Equivalent to roughly $100k+ of professional development work has already been completed in-house. A pro shop would refactor this — not throw it out.
30
screens already built
20
service classes
11
Firestore data models
$100k+
equivalent dev value
Already integrated and working:
Flutter mobile app · Next.js web app · Firebase Auth + Firestore + Storage + Cloud Functions · Stripe payments · NFC scan + cryptographic verification · Evolution engine viewer
2 / 12
Hitbox · From Prototype to Production

## Slide 3
HITBOX
THE GAP TO PRODUCTION
Six things still required to ship.
Same stack, same product. What an external partner brings is execution discipline at production scale.
1
Architecture
Reshape the dependency graph so feature #50 doesn’t break feature #3.
2
Testing & CI
Unit, widget, and integration tests run automatically on every commit.
3
Security & crypto
Patent 1 NFC auth path. Amateur mistakes cause chip cloning and replay attacks.
4
Production hardening
Errors, retries, offline mode, observability (Sentry / Crashlytics), abuse limits.
5
Performance
List virtualization, image caching, cold-start time, bundle size.
6
Design polish
Every screen state designed in Figma before any code. Highest-ROI single spend.
3 / 12
Hitbox · From Prototype to Production

## Slide 4
HITBOX
PATH FORWARD
Six phases. Funded in stages, not one fat contract.
0
Scope finalization
Cut features. Pick first platform.
2 wk
$0
1
Design system & UX
Figma + every screen state.
3–4 wk
$15–25k
2
Discovery & fixed bid
Senior contractor audit + scope quote.
2–3 wk
$5–10k
3
Build v1 of one client
Refactor + harden, ship to App Store or Vercel.
10–16 wk
$60–80k
4
Ship the second client
Other platform on the now-hardened backend.
8–12 wk
$50–80k
5
IP-critical hardening
Crypto + evolution security review.
2–4 wk
$15–25k
Total to launch (mid-point ~$180k)
$145–220k
4 / 12
Hitbox · From Prototype to Production

## Slide 5
HITBOX
PHASE 0
0
Scope finalization
Two weeks of internal work to lock the launch feature set before any vendor is engaged.
ACTIVITIES
Audit the current feature list against the implementation guide
Sort every feature into Launch (8–12 items only), V1.1, or Later
Decide first launch platform — mobile (NFC differentiator) or web (broader reach)
Identify the buyer cohort for the soft launch
Approve the resulting scope document with leadership
INVESTMENT
$0
Internal work — no external spend.
TIMELINE
2 weeks
OWNER
Founder + leadership
DELIVERABLE
Written scope: Launch / V1.1 / Later feature buckets, plus a chosen first platform.
WHY THIS MATTERS
Every feature cut at this phase saves roughly $5–15k downstream. Skipping this is the most expensive mistake possible.
5 / 12
Hitbox · From Prototype to Production

## Slide 6
HITBOX
PHASE 1
1
Design system & UX
A senior product designer produces every screen state and a documented brand-aligned design system.
ACTIVITIES
Design every Launch-bucket screen in every state (loading, empty, error, success)
Document brand-aligned design system (Kinetic Etherealism: indigo, lavender, cyan, rose)
Specify motion, micro-interactions, and component states
Build a Figma component library for engineering reuse
Conduct two design review cycles with leadership before sign-off
INVESTMENT
$15–25k
Mid-point ~$20k.
TIMELINE
3–4 weeks
OWNER
Senior product designer (Figma)
DELIVERABLE
Full Figma file + design system tokens, ready for engineering hand-off.
WHY THIS MATTERS
Highest single ROI in the entire plan. Without it, developers make UX decisions at $150/hr — usually badly, always expensively.
6 / 12
Hitbox · From Prototype to Production

## Slide 7
HITBOX
PHASE 2
2
Discovery & fixed bid
A trusted senior contractor audits the existing codebase and produces a written, fixed-bid scope.
ACTIVITIES
Read and audit the existing Flutter, Next.js, and Cloud Functions code
Identify gaps to production: testing, security, performance, observability
Produce a milestone-based scope document with clear acceptance criteria
Issue a fixed-bid quote — not time-and-materials — for Phases 3 and 4
Recommend the development team structure and seniority mix
INVESTMENT
$5–10k
Mid-point ~$7.5k.
TIMELINE
2–3 weeks
OWNER
Independent senior contractor
DELIVERABLE
Technical audit + production gap analysis + fixed-bid quote with milestone plan.
WHY THIS MATTERS
This single step is what protects the budget. Skipping it is how a $100k contract becomes $280k in invoices.
7 / 12
Hitbox · From Prototype to Production

## Slide 8
HITBOX
PHASE 3
3
Build v1 of one client
Refactor and harden the chosen client (mobile or web) to production quality. Ship to store.
ACTIVITIES
Refactor service layer and reshape Firestore schema for scale
Add unit, widget, and integration tests with continuous integration
Wire up observability: Sentry / Crashlytics, structured logging, alerting
Harden error handling, offline mode, retries, and abuse rate-limits
Implement designs from Phase 1 in full fidelity across every screen state
Ship to TestFlight + Play Store internal track, then phased public rollout
INVESTMENT
$60–80k
Mid-point ~$70k. Largest single line item.
TIMELINE
10–16 weeks
OWNER
External build team (2–3 engineers + PM)
DELIVERABLE
Production app live on the App Store + Google Play, or on Vercel for web.
WHY THIS MATTERS
This is when the prototype becomes a shippable product. Tests, observability, and crash reporting eliminate the production risk we cannot carry today.
8 / 12
Hitbox · From Prototype to Production

## Slide 9
HITBOX
PHASE 4
4
Ship the second client
With the backend already production-hardened, the second client runs faster and cheaper.
ACTIVITIES
Reuse the design system tokens and components from Phase 1
Reuse the backend services, schemas, and Cloud Functions from Phase 3
Build the second client to feature parity for Launch-bucket scope
Cross-platform integration tests: ownership, trades, evolution flows
Coordinated launch checklist, App Store review prep (or DNS / SEO)
INVESTMENT
$50–80k
Mid-point ~$65k. Cheaper than Phase 3 thanks to shared backend + design system.
TIMELINE
8–12 weeks
OWNER
Same build team or rotated team
DELIVERABLE
Both mobile and web clients live in production, on the same Firebase backend.
WHY THIS MATTERS
We need both clients to capture the full audience: collectors who tap NFC chips and casual buyers who arrive via web search.
9 / 12
Hitbox · From Prototype to Production

## Slide 10
HITBOX
PHASE 5
5
IP-critical hardening
Independent security review of the Patent 1 NFC cryptographic path and Patent 2 evolution engine.
ACTIVITIES
Threat-model the physical → NFC → app → backend flow end-to-end
Review cryptographic protocol implementation for weaknesses
Test resistance to chip cloning, replay attacks, and key extraction
Audit the Patent 2 evolution engine for tampering and race conditions
Document the security posture for ongoing development hand-off
INVESTMENT
$15–25k
Mid-point ~$20k. Cannot be skipped.
TIMELINE
2–4 weeks
OWNER
Security engineer or audit firm (e.g. Trail of Bits, Doyensec)
DELIVERABLE
Written security report + remediated code + signed off-going security posture.
WHY THIS MATTERS
Chip cloning, replay attacks, or key leakage destroy the authenticity story that is the entire reason Hitbox is patented.
10 / 12
Hitbox · From Prototype to Production

## Slide 11
HITBOX
INVESTMENT SUMMARY
$145–220k to ship.
Mid-point recommendation: $180k, paid in stages tied to phase milestones.
Chart: 
| P0 Scope | P1 Design | P2 Discovery | P3 Build v1 | P4 Second client | P5 IP audit
Mid-point cost ($k) | 0 | 20 | 7.5 | 70 | 65 | 20
LOW · MID · HIGH
$145k / $180k / $220k
Phase 0 — Scope
$0
Phase 1 — Design
$15–25k
Phase 2 — Discovery
$5–10k
Phase 3 — Build v1
$60–80k
Phase 4 — Second client
$50–80k
Phase 5 — IP hardening
$15–25k
ONGOING (post-launch)
$5–10k / month
11 / 12
Hitbox · From Prototype to Production

## Slide 12
HITBOX
RECOMMENDATION
Approve a $180k staged investment to launch.
$100k+ of equivalent dev value already invested in-house. The path to launch is well-defined, phased, and protected from scope creep.
1
Approve Phase 1 design budget ($15–25k) to begin in 2 weeks.
2
Schedule Phase 0 scope-lock review with leadership this month.
3
Identify and contract the senior auditor for Phase 2 fixed bid.
4
Stand up monthly steering review tied to phase milestones.
5
Target soft launch within 9 months of Phase 3 kick-off.
12 / 12
Hitbox · From Prototype to Production